## 0000_ Sample Site - Schedule
Status | Computed Status | % Complete | Tasks | Duration | Start Date | End Date | Completion Date | Predecessors | MANUFACTURER | Assigned To | Baseline Start | Baseline Finish | Variance | Ready to Start | Notes
In Progress |  | 14% | Boiler Island | 213d | 2030-01-25 | 2030-11-19 |  |  | Garnet Motor Works | Casey Example | 2030-01-29 | 2030-11-19 | 0d | -6
In Progress |  | 42% | Engineering | 167d | 2030-01-25 | 2030-09-16 |  |  |  | Alex Example | 2030-02-22 | 2030-09-23 | -5d
Complete |  | 100% | Mechanical | 4 | 2030-04-24 | 2030-04-29 |  |  | Garnet Motor Works | Blake Example | 2030-05-06 | 2030-04-16 | 9d | 83
Complete |  | 100% | Submit documentation for day tank | 2d | 2030-04-24 | 2030-04-25 | 2030-04-25 |  | Garnet Motor Works | Alex Example | 2030-05-06 | 2030-04-25 | 0d | 83
Complete |  | 100% | Fabricate pressure transmitters | 4d | 2030-04-24 | 2030-04-29 | 2030-04-29 |  | Garnet Motor Works | Alex Example | 2030-05-15 | 2030-04-18 | 7d | 83
Complete |  | 100% | Electrical | 22d | 2030-02-12 | 2030-03-13 |  |  | Garnet Motor Works | Alex Example | 2030-02-22 | 2030-02-14 | 19d | 12
Complete |  | 100% | Submit documentation for burner skid | 5d | 2030-02-12 | 2030-02-18 | 2030-02-18 | 6 | Garnet Motor Works | Alex Example | 2030-03-12 | 2030-03-04 | -10d | 12
Complete |  | 100% | Submit documentation for expansion joints | 3d | 2030-02-19 | 2030-02-21 | 2030-02-21 | 8 | Garnet Motor Works | Alex Example | 2030-03-01 | 2030-03-07 | -10d | 19
Complete |  | 100% | Submit documentation for isolation valves | 1d | 2030-02-19 | 2030-02-19 | 2030-02-19 | 9 | Garnet Motor Works | Alex Example | 2030-03-07 | 2030-03-19 | -20d | 19
Complete |  | 100% | Inspect fuel gas train | 4d | 2030-02-19 | 2030-02-22 | 2030-02-22 | 10 | Garnet Motor Works | Alex Example | 2030-03-19 | 2030-03-15 | -15d | 19
Complete |  | 100% | Review drawings for isolation valves | 2d | 2030-02-22 | 2030-02-25 | 2030-02-25 |  | Garnet Motor Works | Alex Example | 2030-03-01 | 2030-03-07 | -8d | 22
Complete |  | 100% | Review drawings for pressure transmitters | 4d | 2030-02-26 | 2030-03-01 | 2030-03-01 |  | Garnet Motor Works | Alex Example | 2030-03-26 | 2030-03-22 | -15d | 26
Complete |  | 100% | Submit documentation for control panel | 6d | 2030-03-01 | 2030-03-08 | 2030-03-08 | 13FF | Garnet Motor Works | Alex Example | 2030-03-19 | 2030-03-22 | -10d | 29
Complete |  | 100% | Commission feedwater pump set | 3d | 2030-03-11 | 2030-03-13 | 2030-03-13 |  | Garnet Motor Works | Alex Example | 2030-03-13 | 2030-03-27 | -10d | 39
Complete |  | 100% | Deliver control panel | 4d | 2030-03-13 | 2030-03-18 | 2030-03-18 | 15FF |  | Casey Example | 2030-03-13 | 2030-03-28 | -8d | 41
Complete |  | 100% | Inspect feedwater pump set | 3d | 2030-03-19 | 2030-03-21 | 2030-03-21 | 16FF |  |  | 2030-03-26 | 2030-04-04 | -10d
In Progress |  | 71% | Piping | 6d | 2030-01-25 | 2030-02-01 |  |  | Garnet Motor Works | Alex Example | 2030-01-29 | 2030-03-01 | -20d | -6
Complete |  | 100% | Install flow meters | 4d | 2030-01-25 | 2030-01-30 | 3 days |  | Garnet Motor Works | Alex Example | 2030-01-25 | 2030-01-30 | 0d | -6
Complete |  | 100% | Deliver pressure transmitters | 1d | 2030-01-30 | 2030-01-30 |  | 19 | Garnet Motor Works | Alex Example | 2030-01-30 | 2030-02-06 | -5d | -1
In Progress |  | 12% | Inspect fuel gas train | 3d | 2030-01-30 | 2030-02-01 |  | 20 | Garnet Motor Works | Alex Example | 2030-01-30 | 2030-02-06 | -3d | -1
In Progress |  | 1% | Instrumentation | 72 | 2030-06-07 | 2030-09-16 |  |  |  |  | 2030-07-05 | 2030-10-02 | -12d | 127
In Progress |  | 12% | Submit documentation for feedwater pump set | 5d | 2030-06-12 | 2030-06-18 |  | 21 | Garnet Motor Works | Alex Example | 2030-06-12 | 2030-06-25 | -5d | 132
Not Started |  | 0% | Fabricate pilot assembly | 6d | 2030-06-19 | 2030-06-26 |  | 23 | Garnet Motor Works | Alex Example | 2030-06-26 | 2030-06-26 | 0d | 139
Not Started |  | 0% | Submit documentation for stack and damper | 1d | 2030-06-21 | 2030-06-21 |  |  | Garnet Motor Works | Alex Example | 2030-07-12 | 2030-06-21 | 0d | 141
Not Started |  | 0% | Receive isolation valves | 3w | 2030-06-21 | 2030-07-11 |  | 25 | Garnet Motor Works | Alex Example | 2030-06-21 | 2030-07-11 | 0d | 141
Not Started |  | 0% | Deliver pilot assembly | 1w | 2030-07-12 | 2030-07-18 |  | 26FS +3d | Garnet Motor Works | Alex Example | 2030-07-19 | 2030-07-23 | -3d | 162
Not Started |  | 0% | Test burner skid | 1w | 2030-07-15 | 2030-07-19 |  |  | Garnet Motor Works | Alex Example | 2030-07-22 | 2030-07-19 | 0d | 165
Not Started |  | 0% | Isolation valves | 72 | 2030-06-07 | 2030-09-16 |  |  |  | Blake Example | 2030-07-05 | 2030-09-12 | 2d | 127
Not Started |  | 0% | Fabricate isolation valves | 1d | 2030-09-16 | 2030-09-16 |  | 28FF | Hollis Thermal | Emery Example | 2030-09-16 | 2030-08-27 | 14d | 228
Not Started |  | 0% | Control panel | 9d | 2030-06-07 | 2030-06-19 |  |  |  |  | 2030-06-19 | 2030-05-23 | 19d | 127
Not Started |  | 0% | Install control panel | 6d | 2030-06-07 | 2030-06-14 |  | 30 | Ironbark Strainers | Emery Example | 2030-07-05 | 2030-07-12 | -20d | 127
Not Started |  | 0% | Inspect control panel | 4d | 2030-06-14 | 2030-06-19 |  | 32FS +4d | Ironbark Strainers | Emery Example | 2030-07-12 | 2030-06-19 | 0d | 134
Not Started |  | 0% | Deliver economizer | 4d | 2030-06-19 | 2030-06-24 |  | 33 | Ironbark Strainers | Emery Example | 2030-06-19 | 2030-07-01 | -5d | 139
Not Started |  | 0% | Structural | 90 | 2030-02-13 | 2030-06-18 |  |  |  | Drew Example | 2030-03-06 | 2030-06-12 | 4d | 13
Not Started |  | 0% | Install pilot assembly | 4d | 2030-06-07 | 2030-06-12 |  |  | Ironbark Strainers | Emery Example | 2030-06-25 | 2030-06-17 | -3d | 127
Not Started |  | 0% | Review drawings for pressure transmitters | 2d | 2030-06-12 | 2030-06-13 |  | 36 | Ironbark Strainers | Emery Example | 2030-06-28 | 2030-06-13 | 0d | 132
Not Started |  | 0% | Deliver feedwater pump set | 2d | 2030-06-13 | 2030-06-14 |  | 37 | Ironbark Strainers | Emery Example | 2030-07-11 | 2030-07-12 | -20d | 133
Not Started |  | 0% | Commission expansion joints | 1d | 2030-06-13 | 2030-06-13 |  |  | Ironbark Strainers | Emery Example | 2030-07-04 | 2030-07-01 | -12d | 133
Not Started |  | 0% | Receive feedwater pump set | 2d | 2030-06-13 | 2030-06-14 |  | 39 | Ironbark Strainers | Emery Example | 2030-06-13 | 2030-06-19 | -3d | 133
Not Started |  | 0% | Commission economizer | 3d | 2030-06-14 | 2030-06-18 |  |  | Ironbark Strainers | Emery Example | 2030-06-18 | 2030-06-18 | 0d | 134
Not Started |  | 0% | Deaerator | 8 | 2030-02-13 | 2030-02-22 |  |  |  |  | 2030-02-13 | 2030-02-27 | -3d | 13
Not Started |  | 0% | Install deaerator | 1d | 2030-02-13 | 2030-02-13 |  | 41 | Garnet Motor Works | Blake Example | 2030-03-13 | 2030-02-25 | -8d | 13
Not Started |  | 0% | Receive deaerator | 4d | 2030-02-13 | 2030-02-18 |  | 43 | Garnet Motor Works | Blake Example | 2030-03-13 | 2030-03-18 | -20d | 13
Not Started |  | 0% | Order deaerator | 4d | 2030-02-19 | 2030-02-22 |  | 44 | Garnet Motor Works | Blake Example | 2030-03-19 | 2030-03-08 | -10d | 19
Not Started |  | 0% | Review drawings for feedwater pump set | 2d | 2030-02-22 | 2030-02-25 |  | 45 |  |  | 2030-03-22 | 2030-03-25 | -20d | 22
Not Started |  | 0% | Procurement | 201 | 2030-02-12 | 2030-11-19 |  |  | Garnet Motor Works | Emery Example | 2030-02-28 | 2030-11-19 | 0d | 12
Not Started |  | 0% | Documentation | 135 | 2030-04-03 | 2030-10-08 |  |  | Garnet Motor Works | Blake Example | 2030-05-01 | 2030-10-11 | -3d | 62
Not Started |  | 0% | Deliver feedwater pump set | 2d | 2030-08-29 | 2030-08-30 |  |  | Garnet Motor Works | Blake Example | 2030-08-29 | 2030-09-17 | -12d | 210
Not Started |  | 0% | Day tank | 7 | 2030-08-13 | 2030-08-21 |  |  |  |  | 2030-08-23 | 2030-08-26 | -3d | 194
Not Started |  | 0% | Deliver day tank | 5d | 2030-08-13 | 2030-08-19 |  | 49 | Cedar Flow Systems | Emery Example | 2030-09-03 | 2030-09-04 | -12d | 194
Not Started |  | 0% | Fabricate day tank | 5d | 2030-08-14 | 2030-08-20 |  |  | Cedar Flow Systems | Emery Example | 2030-09-11 | 2030-08-27 | -5d | 195
Not Started |  | 0% | Submit documentation for day tank | 5d | 2030-08-15 | 2030-08-21 |  |  | Cedar Flow Systems | Emery Example | 2030-09-05 | 2030-08-26 | -3d | 196
Not Started |  | 0% | Pressure transmitters | 2d | 2030-09-10 | 2030-09-11 |  |  | Northgate Fittings | Casey Example | 2030-09-12 | 2030-09-16 | -3d | 222
Not Started |  | 0% | Fabricate pressure transmitters | 2d | 2030-09-10 | 2030-09-11 |  | 52, 53 | Northgate Fittings | Casey Example | 2030-10-01 | 2030-09-27 | -12d | 222
Not Started |  | 0% | Test pressure transmitters | 1d | 2030-09-10 | 2030-09-10 |  |  | Northgate Fittings | Casey Example | 2030-10-01 | 2030-09-20 | -8d | 222
Not Started |  | 0% | Stack and damper | 11d | 2030-04-03 | 2030-04-17 |  |  | Birchwood Controls | Alex Example | 2030-04-03 | 2030-05-01 | -10d | 62
Not Started |  | 0% | Order stack and damper | 1w | 2030-04-03 | 2030-04-09 |  |  | Birchwood Controls | Finley Example | 2030-04-15 | 2030-04-19 | -8d | 62
Not Started |  | 0% | Install stack and damper | 6d | 2030-04-10 | 2030-04-17 |  | 58FS +5d | Birchwood Controls | Finley Example | 2030-05-08 | 2030-04-17 | 0d | 69
Not Started |  | 0% | Expansion joints | 9d | 2030-08-08 | 2030-08-20 |  |  |  | Casey Example | 2030-08-08 | 2030-09-05 | -12d | 189
Not Started |  | 0% | Order expansion joints | 4d | 2030-08-08 | 2030-08-13 |  | 59 | Marlow Heaters | Alex Example | 2030-08-15 | 2030-09-03 | -15d | 189
Not Started |  | 0% | Receive expansion joints | 5d | 2030-08-14 | 2030-08-20 |  |  | Marlow Heaters | Alex Example | 2030-08-16 | 2030-08-30 | -8d | 195
Not Started |  | 0% | Feedwater pump set | 19d | 2030-06-19 | 2030-07-15 |  |  | Cedar Flow Systems | Alex Example | 2030-06-21 | 2030-07-18 | -3d | 139
Not Started |  | 0% | Submit documentation for feedwater pump set | 5d | 2030-06-19 | 2030-06-25 |  | 62 | Cedar Flow Systems | Casey Example | 2030-06-19 | 2030-06-21 | 2d | 139
Not Started |  | 0% | Submit documentation for feedwater pump set | 3w | 2030-06-25 | 2030-07-15 |  | 64 | Cedar Flow Systems | Casey Example | 2030-07-02 | 2030-07-31 | -12d | 145
Not Started |  | 0% | Economizer | 8 | 2030-04-26 | 2030-05-07 |  |  | Fernhill Instruments |  | 2030-05-24 | 2030-05-10 | -3d | 85
Not Started |  | 0% | Commission economizer | 1w | 2030-04-26 | 2030-05-02 |  | 65 | Fernhill Instruments | Finley Example | 2030-05-08 | 2030-05-20 | -12d | 85
Not Started |  | 0% | Commission economizer | 4d | 2030-05-02 | 2030-05-07 |  | 67 | Fernhill Instruments | Finley Example | 2030-05-06 | 2030-05-23 | -12d
Not Started |  | 0% | Strainer group | 10d | 2030-09-25 | 2030-10-08 |  |  |  | Casey Example | 2030-10-11 | 2030-10-15 | -5d | 237
Not Started |  | 0% | Fabricate strainer group | 2w | 2030-09-25 | 2030-10-08 |  |  | Ironbark Strainers | Casey Example | 2030-10-11 | 2030-11-05 | -20d | 237
Not Started |  | 0% | Order strainer group | 5d | 2030-10-01 | 2030-10-07 |  | 70FS +1d | Ironbark Strainers | Casey Example | 2030-10-11 | 2030-10-28 | -15d | 243
Not Started |  | 0% | Mechanical | 29 | 2030-05-20 | 2030-06-27 |  |  | Ironbark Strainers | Casey Example | 2030-06-05 | 2030-07-15 | -12d | 109
Not Started |  | 0% | Receive control panel | 1w | 2030-05-20 | 2030-05-24 |  | 71 | Ironbark Strainers | Casey Example | 2030-06-17 | 2030-06-14 | -15d | 109
Not Started |  | 0% | Receive control panel | 4d | 2030-05-27 | 2030-05-30 |  |  | Ironbark Strainers | Casey Example | 2030-06-06 | 2030-06-04 | -3d | 116
Not Started |  | 0% | Order stack and damper | 3w | 2030-05-28 | 2030-06-17 |  | 74 | Ironbark Strainers | Casey Example | 2030-05-30 | 2030-07-08 | -15d | 117
Not Started |  | 0% | Deliver day tank | 5d | 2030-06-05 | 2030-06-11 |  | 75FF | Ironbark Strainers | Casey Example | 2030-06-05 | 2030-06-11 | 0d | 125
Not Started |  | 0% | Commission isolation valves | 2d | 2030-06-11 | 2030-06-12 |  | 76 | Ironbark Strainers | Casey Example | 2030-06-13 | 2030-06-26 | -10d | 131
Not Started |  | 0% | Inspect burner skid | 5d | 2030-06-13 | 2030-06-19 |  |  | Ironbark Strainers | Casey Example | 2030-06-13 | 2030-06-24 | -3d | 133
Not Started |  | 0% | Review drawings for isolation valves | 6d | 2030-06-20 | 2030-06-27 |  | 78 | Ironbark Strainers | Casey Example | 2030-06-20 | 2030-07-11 | -10d | 140
Not Started |  | 0% | Electrical | 175d | 2030-02-12 | 2030-10-14 |  |  | Ironbark Strainers |  | 2030-02-22 | 2030-11-04 | -15d | 12
Not Started |  | 0% | Commission burner skid | 2d | 2030-02-12 | 2030-02-13 |  |  | Ironbark Strainers | Casey Example | 2030-03-12 | 2030-01-24 | 14d | 12
Not Started |  | 0% | Fuel gas train | 2 | 2030-10-01 | 2030-10-02 |  |  |  |  | 2030-10-01 | 2030-10-18 | -12d | 243
Not Started |  | 0% | Install fuel gas train | 2d | 2030-10-01 | 2030-10-02 |  | 81 | Fernhill Instruments | Finley Example | 2030-10-11 | 2030-10-07 | -3d | 243
Not Started |  | 0% | Install feedwater pump set | 2w | 2030-10-01 | 2030-10-14 |  | 83 | Fernhill Instruments | Finley Example | 2030-10-17 | 2030-10-17 | -3d | 243
Not Started |  | 0% | Piping | 49 | 2030-09-12 | 2030-11-19 |  |  | Fernhill Instruments | Finley Example | 2030-09-12 | 2030-11-19 | 0d | 224
Not Started |  | 0% | Blowdown tank | 49 | 2030-09-12 | 2030-11-19 |  |  | Ironbark Strainers |  | 2030-09-30 | 2030-12-05 | -12d | 224
Not Started |  | 0% | Test blowdown tank | 3d | 2030-09-12 | 2030-09-16 |  |  | Ironbark Strainers | Finley Example | 2030-09-12 | 2030-08-20 | 19d | 224
Not Started |  | 0% | Install blowdown tank | 4d | 2030-09-16 | 2030-09-19 |  | 87 | Ironbark Strainers | Finley Example | 2030-09-16 | 2030-09-19 | 0d | 228
Not Started |  | 0% | Fabricate blowdown tank | 4d | 2030-09-19 | 2030-09-24 |  | 88 | Ironbark Strainers | Finley Example | 2030-09-23 | 2030-09-27 | -3d | 231
Not Started |  | 0% | Inspect blowdown tank | 6d | 2030-09-25 | 2030-10-02 |  | 89 | Ironbark Strainers | Finley Example | 2030-09-25 | 2030-10-30 | -20d | 237
Not Started |  | 0% | Fabricate blowdown tank | 4d | 2030-10-03 | 2030-10-08 |  | 90 | Ironbark Strainers | Finley Example | 2030-10-03 | 2030-10-22 | -10d | 245
Not Started |  | 0% | Order blowdown tank | 1d | 2030-10-04 | 2030-10-04 |  | 91 | Ironbark Strainers | Finley Example | 2030-10-25 | 2030-10-04 | 0d | 246
Not Started |  | 0% | Order blowdown tank | 3d | 2030-10-07 | 2030-10-09 |  | 92 | Ironbark Strainers | Finley Example | 2030-10-28 | 2030-10-23 | -10d | 249
Not Started |  | 0% | Deliver blowdown tank | 3w | 2030-10-09 | 2030-10-29 |  | 93 | Ironbark Strainers | Finley Example | 2030-10-21 | 2030-10-29 | 0d | 251
Not Started |  | 0% | Test blowdown tank | 1d | 2030-10-29 | 2030-10-29 |  | 94 | Ironbark Strainers | Finley Example | 2030-11-14 | 2030-11-01 | -3d | 271
Not Started |  | 0% | Receive blowdown tank | 1w | 2030-10-29 | 2030-11-04 |  | 95 | Ironbark Strainers | Finley Example | 2030-10-29 | 2030-11-18 | -10d | 271
Not Started |  | 0% | Inspect blowdown tank | 1d | 2030-10-30 | 2030-10-30 |  |  | Ironbark Strainers | Finley Example | 2030-10-30 | 2030-10-30 | 0d | 272
Not Started |  | 0% | Submit documentation for blowdown tank | 2d | 2030-10-30 | 2030-10-31 |  |  | Ironbark Strainers | Finley Example | 2030-11-01 | 2030-10-04 | 19d | 272
Not Started |  | 0% | Review drawings for blowdown tank | 1w | 2030-10-30 | 2030-11-05 |  | 98 | Ironbark Strainers | Finley Example | 2030-10-30 | 2030-11-05 | 0d | 272
Not Started |  | 0% | Test blowdown tank | 2d | 2030-10-31 | 2030-11-01 |  | 99 | Ironbark Strainers | Finley Example | 2030-11-28 | 2030-11-06 | -3d | 273
Not Started |  | 0% | Receive blowdown tank | 1d | 2030-11-01 | 2030-11-01 |  | 100 | Ironbark Strainers | Finley Example | 2030-11-05 | 2030-11-29 | -20d
Not Started |  | 0% | Deliver blowdown tank | 5d | 2030-11-01 | 2030-11-07 |  | 101 | Ironbark Strainers | Finley Example | 2030-11-05 | 2030-11-19 | -8d | 274
Not Started |  | 0% | Fabricate blowdown tank | 1d | 2030-11-04 | 2030-11-04 |  | 102 | Ironbark Strainers | Finley Example | 2030-11-20 | 2030-11-25 | -15d | 277
Not Started |  | 0% | Inspect blowdown tank | 3d | 2030-11-04 | 2030-11-06 |  | 103 | Ironbark Strainers | Finley Example | 2030-11-25 | 2030-11-18 | -8d | 277
Not Started |  | 0% | Fabricate blowdown tank | 3d | 2030-11-07 | 2030-11-11 |  |  | Ironbark Strainers | Finley Example | 2030-11-11 | 2030-12-02 | -15d | 280
Not Started |  | 0% | Review drawings for blowdown tank | 5d | 2030-11-11 | 2030-11-15 |  | 105 | Ironbark Strainers | Finley Example | 2030-11-27 | 2030-11-22 | -5d | 284
Not Started |  | 0% | Receive blowdown tank | 3d | 2030-11-15 | 2030-11-19 |  | 106 | Ironbark Strainers | Finley Example | 2030-12-13 | 2030-12-17 | -20d | 288
Not Started |  | 0% | Deliver blowdown tank | 1d | 2030-11-15 | 2030-11-15 |  | 107 | Ironbark Strainers | Finley Example | 2030-11-15 | 2030-12-13 | -20d
Not Started |  | 0% | Install blowdown tank | 2d | 2030-11-15 | 2030-11-18 |  | 108 | Ironbark Strainers | Finley Example | 2030-12-13 | 2030-12-09 | -15d | 288
Not Started |  | 0% | Test blowdown tank | 1d | 2030-11-18 | 2030-11-18 |  | 109 | Ironbark Strainers | Finley Example | 2030-12-04 | 2030-11-25 | -5d | 291
Not Started |  | 0% | Instrumentation | 44d | 2030-03-04 | 2030-05-02 |  |  |  | Finley Example | 2030-03-04 | 2030-04-26 | 4d | 32
Not Started |  | 0% | Receive blowdown tank | 6d | 2030-03-04 | 2030-03-11 |  |  | Ironbark Strainers | Finley Example | 2030-03-14 | 2030-03-14 | -3d | 32
Not Started |  | 0% | Inspect isolation valves | 2w | 2030-03-12 | 2030-03-25 |  |  | Ironbark Strainers | Finley Example | 2030-03-12 | 2030-04-01 | -5d | 40
Not Started |  | 0% | Receive expansion joints | 4d | 2030-03-26 | 2030-03-29 |  | 113 | Ironbark Strainers | Finley Example | 2030-04-05 | 2030-04-26 | -20d | 54
Not Started |  | 0% | Receive pressure transmitters | 6d | 2030-03-29 | 2030-04-05 |  | 114 | Ironbark Strainers | Finley Example | 2030-04-05 | 2030-04-12 | -5d | 57
Not Started |  | 0% | Order control panel | 1d | 2030-04-05 | 2030-04-05 |  | 115 | Ironbark Strainers | Finley Example | 2030-04-17 | 2030-03-27 | 7d | 64
Not Started |  | 0% | Inspect economizer | 1d | 2030-04-05 | 2030-04-05 |  | 115, 116 | Ironbark Strainers | Finley Example | 2030-04-17 | 2030-03-21 | 11d | 64
Not Started |  | 0% | Order feedwater pump set | 5d | 2030-04-08 | 2030-04-12 |  | 117 | Ironbark Strainers | Finley Example | 2030-04-08 | 2030-04-26 | -10d | 67
Not Started |  | 0% | Commission isolation valves | 4d | 2030-04-12 | 2030-04-17 |  | 118 | Ironbark Strainers | Finley Example | 2030-04-12 | 2030-05-01 | -10d | 71
Not Started |  | 0% | Submit documentation for deaerator | 3d | 2030-04-18 | 2030-04-22 |  | 119 | Ironbark Strainers | Finley Example | 2030-05-16 | 2030-04-29 | -5d | 77
Not Started |  | 0% | Receive expansion joints | 3d | 2030-04-23 | 2030-04-25 |  | 120 | Ironbark Strainers | Finley Example | 2030-04-23 | 2030-05-23 | -20d | 82
Not Started |  | 0% | Fabricate blowdown tank | 6d | 2030-04-25 | 2030-05-02 |  | 121 | Ironbark Strainers | Finley Example | 2030-04-25 | 2030-05-20 | -12d | 84
Not Started |  | 0% | Structural | 3d | 2030-03-25 | 2030-03-27 |  |  | Ironbark Strainers |  | 2030-04-04 | 2030-04-10 | -10d | 53
Not Started |  | 0% | Test feedwater pump set | 1d | 2030-03-25 | 2030-03-25 |  | 122 | Ironbark Strainers | Finley Example | 2030-04-10 | 2030-03-25 | 0d | 53
Not Started |  | 0% | Order pilot assembly | 3d | 2030-03-25 | 2030-03-27 |  | 124FS +3d | Ironbark Strainers | Finley Example | 2030-04-15 | 2030-04-03 | -5d | 53
Not Started |  | 0% | Review drawings for economizer | 3d | 2030-03-25 | 2030-03-27 |  | 125 | Ironbark Strainers | Finley Example | 2030-03-27 | 2030-04-01 | -3d | 53
Not Started |  | 0% | Deliver flow meters | 1d | 2030-03-25 | 2030-03-25 |  | 126 | Ironbark Strainers | Finley Example | 2030-04-22 | 2030-04-22 | -20d | 53
Not Started |  | 0% | Commission flow meters | 2d | 2030-03-25 | 2030-03-26 |  | 127FS +2d | Ironbark Strainers | Finley Example | 2030-04-04 | 2030-03-06 | 14d | 53
Not Started |  | 0% | Submit documentation for stack and damper | 2w | 2030-03-26 | 2030-04-08 |  | 128 |  | Drew Example | 2030-03-26 | 2030-03-19 | 14d | 54
Not Started |  | 0% | Inspect blowdown tank | 3d | 2030-04-09 | 2030-04-11 |  | 129 |  | Casey Example | 2030-04-19 | 2030-04-29 | -12d | 68
Not Started |  | 0% | Fuel Handling | 9 | 2030-04-11 | 2030-04-23 |  |  |  | Finley Example | 2030-05-02 | 2030-05-03 | -8d | 70
Not Started |  | 0% | Order strainer group | 5d | 2030-04-11 | 2030-04-17 |  |  |  | Alex Example | 2030-05-09 | 2030-04-22 | -3d | 70
Not Started |  | 0% | Receive fuel gas train | 5d | 2030-04-17 | 2030-04-23 |  | 132FF |  |  | 2030-05-03 | 2030-05-09 | -12d | 76
Not Started |  | 0% | Review drawings for day tank | 1d | 2030-04-23 | 2030-04-23 |  |  |  | Finley Example | 2030-05-09 | 2030-04-30 | -5d | 82
Not Started |  | 0% | Submit documentation for blowdown tank | 1d | 2030-04-23 | 2030-04-23 |  | 134FF |  |  | 2030-04-30 | 2030-05-14 | -15d | 82
Not Started |  | 0% | Commission pilot assembly | 1d | 2030-04-23 | 2030-04-23 |  | 134, 135 |  | Finley Example | 2030-05-03 | 2030-04-30 | -5d | 82